## Sheet1
Group name: The 4 Amigos
Members: My Nguyen Brandon Reed Darren Carter Sheridan Seelson
Tasks | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-01 | My
Build a team | [11 empty] | Brandon
Contact info | 2019-03-04: Done | Darren
schedule | 2019-03-04: We agreed that we going to meet up 3:30 every Tuesday until the project is due | Sheridan
assessment | [11 empty] | Everyone | bar: 2019-03-04; 2019-03-25; 2019-04-29
Design
Car | 2019-03-04: Create Car (.png) (32x32 pixels)
Pavement | 2019-03-04: Create Pavement (.png) (32x32 pixels)
Log | 2019-03-04: Create log (.png) (32x32 pixels)
Frog | 2019-03-04: Create the frog (.png) (32x32 pixels)
End Screen | 2019-03-11: Create end screen
Title Screen | 2019-03-11: Create title screen
Turtles | 2019-03-04: Create Turtles (.png) (32x32 pixels)
Font | 2019-03-04: Create the font (.png) (32x32 pixels)
Background (Top and Bottom) | 2019-03-04: Create the top and bottom artifact
Development
Frog movement | 2019-03-18: Darren
obsticles movement | bar: 2019-03-18 to 2019-04-15
Scoring System | 2019-03-18: Brandon
End Screen | bar: 2019-03-18 to 2019-04-15
Start Screen | 2019-03-18: Sheridan
Background | 2019-03-18: Sheridan
Interaction between game's artifacts | 2019-03-18: Brandon
Final design | 2019-04-15: Everyone
Testing | 2019-04-22: Everyone
Desk Checking | 2019-04-29: Everyone
Test for error | 2019-04-29: Everyone
Final Report/Presentation
Writing/Documentation | 2019-02-25: Everyone
Final delivery | 2019-05-01: Everyone
Game Description: A player will control a frog vertically across the screen, the goal is to reach the top of the screen while dodging obsticles. The player will have to complete 5 levels to reach the end game